## Sheet1
| Day6 Alpha | Day 7 | Day 8 Beta | Day 9 Finish | Day 10
Stephanie | Check in with leads Help Zeke with documentation | Check in with leads Help any leads that need it Help Zeke with documentation | Check in with leads Help any leads that need it Help Zeke with documentation | Practice presenting | Present Project
Manny | Continue in mixcraft Implement sounds into Unity | Continue In Mixcraft, Implement Sounds In Unity | Make the last plus sounds Implement | Finishing putting/making all the sounds in unity and making it sound nice | Present
Zeke | Update documentation Assist with Team management Try to help with Cactus Sprite distillation | Update documentation Assist with Team management | Update documentation Assist with Team management | Finalizing documents | Present
Olivia | Aid People in Github or Unity Issues Aid in adding anything into Unity Help make sprite assets if extra time | Aid People in Github or Unity Issues Aid in adding anything into Unity | Aid People in Github or Unity Issues Aid in adding anything into Unity | Finishing touches | Present
Aydan | Work on egg/seed rotation animation Begin implementing sprites into the unity Do dog animation/sprites Do ground sprites | Finish dog animation/sprites Implement more assets into unity | Cover manny in his absence Finish unity sprite implementation for chicken run game | Finalization | Present